| Milestone | Completed |
| --- | --- |
| Recruitment plans are finalized |  |
| All sites identified (documentation of site commitment) |  |
| Methods for accurately identifying participants validated |  |
| All agreements for necessary subcontracts in place (including DUAs if applicable) |  |
| Ethical/regulatory aspects are addressed |  |
| Coordinated IRB oversight in place |  |
| Finalized plans for informed consent or waiver of informed consent |  |
| Finalized data and safety monitoring plan |  |
| Intervention is fully developed and finalized |  |
| Finalized intervention (including materials and training at sites) ready for site implementation |  |
| Finalized protocol is IRB approved (informed consent and data collection forms, if applicable) |  |
| Data collection methods are adequately tested |  |
| Validated methods for extracting and harmonizing electronic health record information |  |
| Validated study surveys, interviews, or other data collection modes |  |
| Demonstrated quality assurance and harmonization of data elements across healthcare systems/sites |  |
| Statistical and data analysis methods have been adequately developed and recorded |  |
| Budget is realistic, feasible, and accounts for potential changes |  |
| Trial registration is updated to reflect any changes to study protocol (including changes to outcome measures and analytic plan) |  |

Implementation Readiness Checklist

Prepared by: NIH Pragmatic Trials Collaboratory Coordinating Center

Version: January 29, 2026